## musician-finder
Musician Finder
UI - User Interface
Name | Subitems | Person | Priority | Status | Item ID (auto generated)
Welcome Page | Register Button, Log In Button, Headline | Lidor I Eliyahu Shelef | High | Approved | 760037526
Log In Page |  | Lidor I Eliyahu Shelef | Low | Approved | 778157430
Register Page |  | Lidor I Eliyahu Shelef | Medium | Approved | 778157665
Publish Yourself | Musician, Band | eliezerRevach | Medium | Working on it | 760321356
Menu | Background, Buttons | Lidor I Eliyahu Shelef | Medium | Approved | 760319185
Private Area | Labels, Inputs, Lists, Buttons | Lidor I Eliyahu Shelef | High | Approved | 760319441
General Search |  | eliezerRevach | Low | Working on it | 760320604
Entrance Page - like most app for 3 seconds |  | Lidor I Eliyahu Shelef | Low | Approved | 767139071
General Chat Area |  | Lidor I Eliyahu Shelef | Medium | Working on it | 764011148
Chat Page |  | Lidor I Eliyahu Shelef | Medium | Done | 782138906
Post Design |  | Lidor I Eliyahu Shelef | Low | In Queue | 778647503
Posts Page |  | Lidor I Eliyahu Shelef | Medium | Working on it | 782138443
UX - User Experience
Name | Subitems | Person | Priority | Status | Item ID (auto generated)
Firabase |  | yisrael | Critical | Approved | 760037527
Welcome Page | Register, Log In | Lidor I Eliyahu Shelef | Medium | Approved | 760037532
Publish Yourself | Musician, Band | yisrael | Medium | Done | 760326151
Menu |  | Lidor I Eliyahu Shelef | Medium | Done | 760325403
Private Area |  | yisrael | High | Approved | 760325550
General Search |  | Or Segal ¦ yisrael | Low | Working on it | 760325690
User |  | yisrael | High | Approved | 760547484
Instruments |  | Lidor I Eliyahu Shelef | High | Approved | 762288636
Configuration | Instruments, Cities, Genres | Lidor I Eliyahu Shelef | High | Approved | 762288767
General Chat Area |  | yisrael | Medium | Waiting for review | 764011172
Entrance Page |  | Lidor I Eliyahu Shelef | Low | Approved | 768397819
posts | Musician Post, Band Post, Sending Post to database, Retrieving Post from database | yisrael | Medium | Approved | 778412158

## musician-finder-updates
Musician Finder | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
760037527 | Firabase | Update |  | yisrael | 24/September/2020 04:08:40 PM | write user to database get users from database | 0 |  | 796425954
760547484 | User | Update |  | yisrael | 24/September/2020 04:10:04 PM | created a user private String UserName ,UserPass , Name , UserBio , UserLink ; private int UserAge ; | 0 |  | 796427178